## Cover Page
TMR Climate Change Risk Assessment And Adaptation Template
This Climate Change Risk Assessment and Adaptation Template is a spreadsheet designed to enable transport infrastructure projects to undertake climate change risk assessments in accordance with the Engineering Policy 170 Climate Change Risk Assessments. The consequence and likelihood statements have been developed from AS 5334 Climate Change Risk Assessments for Human Settlements. The risk statements and treatments have been developed by major transport infrastructure projects (>$100M) that have undertaken climate change risk assessments. These are not provided as a limiting list rather as a starting point to provide guidance and examples to project of what risk treatments may be suitable. Projects can develop their own risk treatments. Consideration should be given to: - the final asset, - network operations and level of service during the operational phase, and - maintenance - discontinuity of assets due to inconsistency of materials and component design can result in difficulties and elevated costs during maintenance operations. Useful resources include: - EP170 Climate Change Risk Assessments Methodology - Climate Change Risk and Adaptation Assessment Framework - Queensland Future Climate Dashboard (https://app.longpaddock.qld.gov.au/dashboard/) For further information please contact PMD Environment, Heritage and Corridor Management.

## Risk Assessment
TMR Climate Change Risk Assessment Template
Instructions: The TMR Climate Change Risk Assessment Tool has been developed based on the Climate Change Risk and Adaptation Assessment Framework. The user shall work through the listed risk statements and workshop within the project team disciplines any other project-specific risks that may arise from climate change. The User shall select the most approproriate likelihod and consequence from the drop down menu. Projects should consider whether the risk statements are applicable to specific assets or whether additional or different risks may apply. Projects can nominate risks as "not applicable" if it is not-applicable to the project and add project-specific risks as they apply. Definitions of the AS 5334 likelihood and consequence categories are provided on the supporting Worksheet. The Risk Rating will then automatically populate from the AS 5334 risk rating matrix. The risk statements have been compiled from major projects that have completed climate change assessments. In particular the M1 Program has contributed considerable work to the development of this template. In undertaking this climate change risk assessment, applicable climate projects and timeframes shall be determined from the site and asset being considered.
Project |  | [insert name of project] | Project Phase |  | [preliminary evaluation, business case, detailed design] |  |  | Version No.
Risk Assessment Participants: |  | [list names] | Approved |  | [signature of project manager] |  |  | Date
Risk ID | Climate change variable | Risk statement | Direct / Indirect | [Short term timeframe eg 2030] |  |  | [longer term timeframe eg 2070]
|  |  |  | Likelihood | Consequence | Risk Rating | Likelihood | Consequence | Risk Rating
Bushfire
BF-1 | Increased risk of bushfire events and weather resulting in: | Damage to electrical infrastructure as a result of ash accumulation (ramp metering, signals and variable speed limit signs), resulting in impacts to operation of the road | Direct |  |  | #N/A |  |  | #N/A
BF-2 |  | Damage to infrastructure (e.g. noise walls, pavement) resulting in increased maintenance and decrease in operational safety | Direct |  |  | #N/A |  |  | #N/A
BF-3 |  | Potential smoke inhalation and health concerns for maintenance workers | Direct |  |  | #N/A |  |  | #N/A
BF-4 |  | Potential smoke inhalation and health concerns for pedestrian / cyclist / vehicle users | Direct |  |  | #N/A |  |  | #N/A
BF-5 |  | Visibility concerns for motorists | Direct |  |  | #N/A |  |  | #N/A
BF-6 |  | Delays to maintenance and operational requirements impacting scheduled activities | Direct |  |  | #N/A |  |  | #N/A
BF-7 |  | Damage to substations and associated infrastructure resulting in disruption of electricity supply with potential power outages and communications network failure | Indirect |  |  | #N/A |  |  | #N/A
BF-8 |  | Loss of access resulting in user delays, emergency vehicle access or additional traffic on surrounding road network | Direct |  |  | #N/A |  |  | #N/A
BF-9 |  | Electrical infrastructure sparking bushfires and subsequent damage (and impact) to surrounding areas | Indirect |  |  | #N/A |  |  | #N/A
BF-10 |  | A loss of access to the surrounding road network, resulting in increased traffic and subsequent safety concerns for motorists along the road | Indirect |  |  | #N/A |  |  | #N/A
BF-11 |  | Fauna and residents using the infrastructure as egress to escape bushfire | Indirect |  |  | #N/A |  |  | #N/A
BF-12 |  | Increased risk of bushfire ignition within roadside vegetation | Direct |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Extreme Storm Events
SE-1 | Increased incidence and severity of storm events (e.g. wind, lightning) resulting in: | Damage to electrical infrastructure from lightning, wind or hail (e.g. ramp metering, lighting, signals and variable speed limit signage) resulting in disruption of road operation | Direct |  |  | #N/A |  |  | #N/A
SE-2 |  | Structural stability concerns and/or impacts for bridge / noise structures - potential for collapse | Direct |  |  | #N/A |  |  | #N/A
SE-3 |  | An increase in the scale and quantity of debris blown onto the road (as well as impacts to vehicles on the road) causing damage/impact to supporting infrastructure and impacting user safety (motorists, cyclists and pedestrians) | Direct |  |  | #N/A |  |  | #N/A
SE-4 |  | An increase to maintenance and operational costs to support routine repair and replacement works | Direct |  |  | #N/A |  |  | #N/A
SE-5 |  | Power outages (black outs) as a result of damage to energy substations and associated energy/electrical infrastructure | Indirect |  |  | #N/A |  |  | #N/A
SE-6 |  | Damage to the surrounding road network, resulting in increased vehicle usage of the motorway and potential decrease in safety due to the increase in usage | Indirect |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Extreme rainfall, flooding and storm events
ERF-1 | Increased incidence of extreme rainfall events and subsequent flooding resulting in: | The capacity of existing drainage infrastructure being exceeded (due to either blockage from debris or volume of water) leading to inundation of surrounding infrastructure (e.g. properties, road, bus stations, kiss and ride, interchanges) | Direct |  |  | #N/A |  |  | #N/A
ERF-2 |  | Exacerbated local flooding risks impacting motorists | Direct |  |  | #N/A |  |  | #N/A
ERF-3 |  | Increased rainfall intensity along the road resulting in increased road incidents (e.g. aquaplaning) and safety risks to motorists | Direct |  |  | #N/A |  |  | #N/A
ERF-4 |  | An increased safety risk and disruption to the users of the cycle / pedestrian network due to inundation of infrastructure | Direct |  |  | #N/A |  |  | #N/A
ERF-5 |  | Water damage to electrical infrastructure (ramp metering, signals and variable speed limit signs) resulting in disruption of road operation | Direct |  |  | #N/A |  |  | #N/A
ERF-6 |  | Erosion of infrastructure foundations resulting in the exposure of concrete (e.g. road base, drainage infrastructure, pier supports), particularly along river and creek crossings | Direct |  |  | #N/A |  |  | #N/A
ERF-7 |  | Increased risk of landslip (e.g. weakened verges and decreased slope stability) in surrounding areas resulting in damage to infrastructure | Direct |  |  | #N/A |  |  | #N/A
ERF-8 |  | Accelerated degradation of assets from increased rainfall intensities and prolonged flooding resulting in increased maintenance and operational costs and repairs | Direct |  |  | #N/A |  |  | #N/A
ERF-9 |  | Increased risk of additional scour and erosional impacts on surrounding waterways and the associated environmental impacts (e.g. water quality, ecological implications for species) | Direct |  |  | #N/A |  |  | #N/A
ERF-10 |  | Increased stormwater flow from surrounding developed areas contributing to additional water volumes in drainage lines and other stormwater infrastructure (e.g. culverts) resulting in additional localised flooding impacts | Indirect |  |  | #N/A |  |  | #N/A
ERF-11 |  | Localised ponding leading to an increased attraction for animals resulting in increased hazards for fauna / automobile accidents. | Indirect |  |  | #N/A |  |  | #N/A
ERF-12 |  | Power outages at substations disrupting supply to electrical and communications systems impacting operation of the road | Indirect |  |  | #N/A |  |  | #N/A
ERF-13 |  | Surrounding areas being inundated, resulting in an increase of motorists using the road as an escape route and potential decrease in safety along the road due to increased traffic in a hazard event | Indirect |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Mean rainfall / Drought
MRD-1 | Changes in mean rainfall levels and increased incidence of drought conditions resulting in: | Soil cracking resulting in damage to infrastructure (e.g. culverts, foundations, road base, embankments) | Direct |  |  | #N/A |  |  | #N/A
MRD-2 |  | Adverse impacts to proposed landscaping areas (including those reinstated) including lack of available water for irrigation | Direct |  |  | #N/A |  |  | #N/A
MRD-3 |  | Wildlife migration to watercourses | Indirect |  |  | #N/A |  |  | #N/A
MRD-4 |  | Increased fuel for bushfire | Indirect |  |  | #N/A |  |  | #N/A
MRD-5 |  | Dust impacts from quarry - skid resistance, visibility and erosion leading to poor water quality | Indirect |  |  | #N/A |  |  | #N/A
MRD-6 |  | Water shortage during prolonged construction phase and operational phase | Indirect |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Sea level rise
SLR-1 | Increasing sea levels resulting in: | Inundation of road formation resulting in disruption to operation | Direct |  |  | #N/A |  |  | #N/A
SLR-2 |  | Permanent inundation of drainage infrastructure reducing the flood immunity of structures | Direct |  |  | #N/A |  |  | #N/A
SLR-3 |  | Exacerbated local flooding risks | Direct |  |  | #N/A |  |  | #N/A
SLR-4 |  | Ingress of saltwater intrusion into embankment and lower pavement layers causing reduced performance life | Direct |  |  | #N/A |  |  | #N/A
SLR-5 |  | Increased incidence of coastal erosion, exposing footings and other buried structures, resulting in damage or potential collapse | Direct |  |  | #N/A |  |  | #N/A
SLR-6 |  | Increased incidence of saltwater intrusion, accelerating corrosion of concrete and steel structures | Direct |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Extreme heat / Solar Radiation
EH-1 | Increased incidence and duration of extreme heat events and solar radiation resulting in: | Damage to electrical system components (e.g. cabling, sensor loops, housings) resulting in disruption smart motorway operation, CCTV and emergency response | Direct |  |  | #N/A |  |  | #N/A
EH-2 |  | The accelerated degradation and malfunctioning of electrical equipment, requiring replacement more often, increasing maintenance and operational costs | Direct |  |  | #N/A |  |  | #N/A
EH-3 |  | The accelerated deterioration of concrete / asphalt infrastructure, resulting in decreased safety for motorists (e.g. potholes) | Direct |  |  | #N/A |  |  | #N/A
EH-4 |  | The accelerated deterioration of concrete / asphalt / steel infrastructure, resulting in increased maintenance and operational costs (e.g. resurfacing) | Direct |  |  | #N/A |  |  | #N/A
EH-5 |  | Steel structures (e.g. expansion joints, guardrails, bridge components) buckling or warping and impacting safety of users | Direct |  |  | #N/A |  |  | #N/A
EH-6 |  | An increased risk of heat stress for cyclists and pedestrians) using the new facilities | Direct |  |  | #N/A |  |  | #N/A
EH-7 |  | An increase in the number of vehicle breakdowns along the road (due to vehicle overheating) resulting in safety concerns and increased requirements for road management | Indirect |  |  | #N/A |  |  | #N/A
EH-8 |  | Adverse impacts to proposed landscaping areas (including those reinstated) including loss of planted species due to ongoing heat exposure | Direct |  |  | #N/A |  |  | #N/A
EH-9 |  | Increased power demand and/or faults in the network resulting in power supply interruptions and/or outages for electrical infrastructure, including CCTV | Indirect |  |  | #N/A |  |  | #N/A
EH-10 |  | An increased risk to workers during operation from heat stroke, heat stress or heat exhaustion resulting in reduced productivity | Direct |  |  | #N/A |  |  | #N/A
EH-11 |  | Increased sag on overhead cables - decreased clearance | Indirect |  |  | #N/A |  |  | #N/A
EH-12 |  | Equipment heat ratings insufficient to meet increased heat | Indirect |  |  | #N/A |  |  | #N/A
EH-12 |  | Reduced safety for travelling public due to ITS outages, debris on road, potential damage to assets |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
Other project climate hazard
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
|  | [Project Specific] |  |  |  | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A

## Adaptation Assessment
TMR Climate Change Adaptation Assessment Template
Instructions: The TMR Climate Change Risk Assessment Tool has been developed based on the Climate Change Risk and Adaptation Assessment Framework. The user shall work through the listed risk statements and workshop within the project team disciplines any other project-specific risks that may arise from climate change. The User shall select the most approproriate likelihod and consequence from the drop down menu. Definitions of the AS 5334 likelihood and consequence categories are provided on the supporting Worksheet. The Risk Rating will then automatically populate from the AS 5334 risk rating matrix. The risk statements have been compiled from major projects that have completed climate change assessments. In particular the M1 Program has contributed considerable work to the development of this template. NOTE: Projects should only include risk statements that have been determined to be applicable to the project from the Risk Assessment worksheet. Projects can amend adaption actions that are not-applicable or not sutiable for the project or asset and add project-specific adaptation actions as they apply.
Project |  | [insert project name] |  |  | Project phase |  |  |  | Version No.
Assessment Participants |  | [list names] |  |  | Approved |  |  |  | Date
Risk ID | Risk statement | 2030 Risk Rating | 2080 Risk Rating | Adaptation Actions | [Short term timeframe] (IE 2030) |  |  | (longer term timeframe) (IE 2070)
[5 empty] | Revised Likelihood | Revised Consequence | Revised Risk Rating | Revised Likelihood | Revised Consequence | Revised Risk Rating
Bushfire
BF-1 | Damage to electrical infrastructure as a result of ash accumulation (ramp metering, signals and variable speed limit signs), resulting in impacts to operation of the road | #N/A | #N/A | • Construct housing for electrical components to protect from weather and atmospheric deposition |  |  | #N/A |  |  | #N/A
BF-2 | Damage to infrastructure (e.g. noise walls, pavement) resulting in increased maintenance and decrease in operational safety | #N/A | #N/A | • Review and if required, revise the TMR Traffic Operations Business Continuity Plan in response to bushfire events to account for climate extremes (increased severity, increased frequency) including provisions for road closures and/or diversions and emergency bays for vehicle breakdowns and/or emergency access • Update maintenance plan to increase the frequency and review of maintenance activities such as pavement repair • Design noise walls to reduce the probability of damage from bushfire risk • Optimise the design of barriers to be multi-purpose (e.g. withstand bushfire and control fauna) • Consider pavement susceptibility to extreme heat. • Consider bridge and culvert materials for suitability to bushfire risk. |  |  | #N/A |  |  | #N/A
BF-3 | Potential smoke inhalation and health concerns for maintenance workers | #N/A | #N/A | • Revise Standard Operation Procedures (e.g. providing correct PPE (respirators)) and Protocols (rescheduling non-essential works) to account for smoke • Incorporate weather projections and procedures (e.g. dry, windy days) into works scheduling |  |  | #N/A |  |  | #N/A
BF-4 | Potential smoke inhalation and health concerns for pedestrian / cyclist / vehicle users | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information Revise the TMR Traffic Operations Business Continuity Plan to account for climate extremes including selective closure of transports corridor during periods of high smoke and response plans for user emergencies (e.g. health-related incident) • Investigate mobile phone reception along corridor to support full coverage as manner of emergency response Revise the TMR Communication Plan / improve notifications and information provided to motorists using the variable message signs |  |  | #N/A |  |  | #N/A
BF-5 | Visibility concerns for motorists | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information to motorists • Revise the TMR Traffic Operations Business Continuity Plan to account for bushfire risk including road closures and/or diversions when visibility becomes limited and emergency bays for vehicle breakdowns • Revise the TMR Communication Plan / improve notifications and information provided to motorists using the variable message signs |  |  | #N/A |  |  | #N/A
BF-6 | Delays to maintenance and operational requirements impacting scheduled activities | #N/A | #N/A | • Update maintenance and operations plans to provide for rescheduling of impacted activities. |  |  | #N/A |  |  | #N/A
BF-7 | Damage to substations and associated infrastructure resulting in disruption of electricity supply with potential power outages and communications network failure | #N/A | #N/A | • Investigate the inclusion of backup power or redundant supply (e.g. uninterruptable power supply) for electrical systems as part of design |  |  | #N/A |  |  | #N/A
BF-8 | Loss of access resulting in user delays, emergency vehicle access or additional traffic on surrounding road network | #N/A | #N/A | • Revise the TMR Traffic Operations Business Continuity Plan to account for known areas of bushfire risk and vegetation including timing for road closures and/or diversions and provision of emergency bays for vehicle breakdowns and/or emergency access • Review the TMR Continuity Network Response Plan to restrict access to critical areas (e.g. shared paths or interchanges) during bushfire events and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
BF-9 | Electrical infrastructure sparking bushfires and subsequent damage (and impact) to surrounding areas | #N/A | #N/A | • Locate intelligent transportation system cabinets and other critical infrastructure in locations outside of bushfire prone areas and away from combustible vegetation • Prepare and implement maintenance regimes for clearing potential fuel load around electrical infrastructure where present within the corridor • Prepare an emergency management plan to restrict access to critical areas (e.g. shared paths) in the event of a bushfire along the corridor and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
BF-10 | A loss of access to the surrounding road network, resulting in increased traffic and subsequent safety concerns for motorists along the road | #N/A | #N/A | • Revise the TMR Traffic Operations Business Continuity Plan to account for known areas of bushfire risk and vegetation including timing for road closures and/or diversions and provision of emergency bays for vehicle breakdowns and/or emergency access • Review the TMR Continuity Network Response Plan to restrict access to critical areas (e.g. shared paths) in the event of a bushfire along the corridor and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
BF-11 | Fauna and residents using the infrastructure as egress to escape bushfire | #N/A | #N/A | • Incorporating fauna fencing and underpasses (crossing points) into the design • Optimise the design of barriers to be multi-purpose (e.g. withstand bushfire and control fauna). |  |  | #N/A |  |  | #N/A
BF-12 | Increased risk of bushfire ignition within roadside vegetation | #N/A | #N/A | • Incorporating fauna fencing and underpasses (crossing points) into the design • Optimise the design of barriers to be multi-purpose (e.g. withstand bushfire and control fauna) |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Extreme Storm Events
SE-1 | Damage to electrical infrastructure from lightning, wind or hail (e.g. ramp metering, lighting, signals and variable speed limit signage) resulting in disruption of road operation | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate change projection Undertake sensitivity checks against modelling utilising RCP 6.0 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model Locate critical electrical / communications infrastructure outside of known low areas and/or flood risk areas as identified in relevant local modelling • Incorporate lightning protection into the gantries and variable message signs (VMS) • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Evaluate design levels for electrical systems for resilience against flooding and rainfall risks • Provide additional coverage (e.g. covers for electrical systems) / protection (e.g. resistant coatings) of critical electrical infrastructure |  |  | #N/A |  |  | #N/A
SE-2 | Structural stability concerns and/or impacts for bridge / noise structures - potential for collapse | #N/A | #N/A | • Locate critical infrastructure outside of known low areas and/or flood risk areas identified in relevant local modelling (e.g. local government) • Apply Road Drainage Manual hydraulic assessment including climate change projection. • Design new bridges and drainage to minimise and mitigate scour • Incorporation of TMR Design Criteria for Bridges and Other Structures (2018) which accounts for climate change Design bridge piles to a Q2000 event • Provide strengthening to existing bridge structures |  |  | #N/A |  |  | #N/A
SE-3 | An increase in the scale and quantity of debris blown onto the road (as well as impacts to vehicles on the road) causing damage/impact to supporting infrastructure and impacting user safety (motorists, cyclists and pedestrians) | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information • Revise the TMR Traffic Operations Business Continuity Plan to account for extreme storms including road closures during storm events and/or diversions when damage / substantial debris has been identified and provision of emergency bays for vehicle breakdowns and/or emergency access • Revise the TMR Communication Plan / improve notifications and information provided to motorists using the variable message signs • Review the TMR Continuity Network Response Plan for provisions such as restricting access to critical areas during storm events (e.g. shared paths) and outline emergency service provisions and response (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
SE-4 | An increase to maintenance and operational costs to support routine repair and replacement works | #N/A | #N/A | • Update Standard Operating Procedures and maintenance plans to increase the frequency and review of maintenance activities and account for an increase in the intensity of storms and associated expected impacts |  |  | #N/A |  |  | #N/A
SE-5 | Power outages (black outs) as a result of damage to energy substations and associated energy/electrical infrastructure | #N/A | #N/A | • Locate critical infrastructure including any power supply infrastructure outside of known low areas and/or flood risk areas identified in relevant local modelling (e.g. local government) • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Investigate the inclusion of backup power or redundant supply (e.g. uninterruptable power supply) for electrical systems as part of design |  |  | #N/A |  |  | #N/A
SE-6 | Damage to the surrounding road network, resulting in increased vehicle usage of the motorway and potential decrease in safety due to the increase in usage | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information including road closures and detour routes • Revise the TMR Traffic Operations Business Continuity Plan to account for extreme storms including road closures during storm events and/or diversions when damage / substantial debris has been identified and provision of emergency bays for vehicle breakdowns and/or emergency access • Revise the TMR Continuity Network Response Plan to restrict access to critical areas during storm events (e.g. shared paths) and outline emergency service provisions and response (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Extreme rainfall, flooding and storm events
ERF-1 | The capacity of existing drainage infrastructure being exceeded (due to either blockage from debris or volume of water) leading to inundation of surrounding infrastructure (e.g. properties, road, bus stations, kiss and ride, interchanges) | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity of 11.4% (RCP 6.0). • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Review and where relevant, change road geometry (such as the gradient, removal of sag curves or vertical elevation in critical areas) to shorten flow paths and reduce risk of motorway inundation • Design and construct larger culverts, without impacting upstream flows, to account for additional surface flow |  |  | #N/A |  |  | #N/A
ERF-2 | Exacerbated local flooding risks impacting motorists | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity. • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Review and where relevant, change road geometry (such as the gradient, removal of sag curves or vertical elevation in critical areas) to shorten flow paths and reduce risk of motorway inundation Design and construct larger culverts, without impacting upstream flows, to account for additional surface flow • Revise the TMR Continuity Network Response Plan to restrict access to interchanges subject to inundation during flood events and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
ERF-3 | Increased rainfall intensity along the road resulting in increased road incidents (e.g. aquaplaning) and safety risks to motorists | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model) • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information • Revise the TMR Traffic Operations Business Continuity Plan to account for extreme rainfall intensities including provisions for road closures and/or diversions and emergency bays for vehicle breakdowns and/or emergency access • Review and where relevant, change road geometry (such as the gradient, removal of sag curves or vertical elevation in critical areas) to shorten flow paths and reduce risk of motorway inundation • Revise the TMR Continuity Network Response Plan to restrict access to interchanges subject to inundation during flood events and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
ERF-4 | An increased safety risk and disruption to the users of the cycle / pedestrian network due to inundation of infrastructure | #N/A | #N/A | • Locate pedestrian / cycle paths outside of known low areas and/or flood risk areas • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information • Revise the TMR Traffic Operations Business Continuity Plan to account for extreme rainfall including selective closure of transports corridor during extreme storms and response plans for user emergencies (e.g. debris incident or injury) • Investigate mobile phone reception along corridor to support full coverage as manner of emergency response |  |  | #N/A |  |  | #N/A
ERF-5 | Water damage to electrical infrastructure (ramp metering, signals and variable speed limit signs) resulting in disruption of road operation | #N/A | #N/A | • Locate critical infrastructure outside of known low areas and/or flood risk areas • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Evaluate design levels for electrical systems for resilience against flooding and rainfall risks • Provide additional coverage (e.g. covers for electrical systems) |  |  | #N/A |  |  | #N/A
ERF-6 | Erosion of infrastructure foundations resulting in the exposure of concrete (e.g. road base, drainage infrastructure, pier supports), particularly along river and creek crossings | #N/A | #N/A | • Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity. • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Design new bridges and drainage to minimise and mitigate scour • Incorporation of TMR Design Criteria for Bridges and Other Structures (2018) which accounts for climate change Provide strengthening to existing bridge structures • Provide additional protection (e.g. resistant coatings) of critical structures (e.g. steel or otherwise) |  |  | #N/A |  |  | #N/A
ERF-7 | Increased risk of landslip (e.g. weakened verges and decreased slope stability) in surrounding areas resulting in damage to infrastructure | #N/A | #N/A | • Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity. • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Locate critical infrastructure outside of known low areas and/or flood risk areas • Update maintenance plan to increase the frequency and review of maintenance activities • Design new bridges and drainage to minimise and mitigate scour • Design bridge piles to a Q2000 event • Provide strengthening to existing bridge structures |  |  | #N/A |  |  | #N/A
ERF-8 | Accelerated degradation of assets from increased rainfall intensities and prolonged flooding resulting in increased maintenance and operational costs and repairs | #N/A | #N/A | • Design new bridges and drainage to minimise and mitigate scour • Revise Standard Operating Procedures to account for climate extremes including increased intensities of rainfall and more frequent inundation of assets • Update maintenance plan to increase the frequency and review of maintenance activities • Provide additional coverage (e.g. covers for electrical systems) / protection (e.g. resistant coatings) of critical structures (e.g. steel or otherwise) |  |  | #N/A |  |  | #N/A
ERF-9 | Increased risk of additional scour and erosional impacts on surrounding waterways and the associated environmental impacts (e.g. water quality, ecological implications for species) | #N/A | #N/A | • Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Design new bridges and drainage to minimise and mitigate scour • Update maintenance plan to increase the frequency and review of maintenance activities • Design and construct larger culverts, without impacting upstream flows, to account for additional surface flow |  |  | #N/A |  |  | #N/A
ERF-10 | Increased stormwater flow from surrounding developed areas contributing to additional water volumes in drainage lines and other stormwater infrastructure (e.g. culverts) resulting in additional localised flooding impacts | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Design and construct larger culverts, without impacting upstream flows, to account for additional surface flow |  |  | #N/A |  |  | #N/A
ERF-11 | Localised ponding leading to an increased attraction for animals resulting in increased hazards for fauna / automobile accidents. | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity • Undertake sensitivity checks against modelling utilising RC P8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model) Incorporating fauna fencing and underpasses (crossing points) into the design |  |  | #N/A |  |  | #N/A
ERF-12 | Power outages at substations disrupting supply to electrical and communications systems impacting operation of the road | #N/A | #N/A | • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Investigate the inclusion of backup power or redundant supply (e.g. uninterruptable power supply) for electrical systems as part of design |  |  | #N/A |  |  | #N/A
ERF-13 | Surrounding areas being inundated, resulting in an increase of motorists using the road as an escape route and potential decrease in safety along the road due to increased traffic in a hazard event | #N/A | #N/A | • Utilise a consolidated flood model based on local government hazard mapping and modelling, which includes storm surge, sea level rise and increased rainfall intensity • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information • Revise the TMR Continuity Network Response Plan to restrict access to critical areas during flooding events (e.g. shared paths) and outline emergency service provisions and response (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Mean rainfall / Drought
MRD-1 | Soil cracking resulting in damage to infrastructure (e.g. culverts, foundations, road base, embankments) | #N/A | #N/A | • Update maintenance plan to increase the frequency and review of maintenance activities |  |  | #N/A |  |  | #N/A
MRD-2 | Adverse impacts to proposed landscaping areas (including those reinstated) including lack of available water for irrigation | #N/A | #N/A | • Select drought tolerant plants that will be able to cope with reduced water availability but that withstand short intense rainfall events. • Consider vegetation fuel load during landscape planning. |  |  | #N/A |  |  | #N/A
MRD-3 | Wildlife migration to watercourses | #N/A | #N/A | • Incorporating fauna fencing and underpasses (crossing points) into the design • Optimise the design of barriers to be multi-purpose (e.g. withstand bushfire and control fauna) |  |  | #N/A |  |  | #N/A
MRD-4 | Increased fuel for bushfire | #N/A | #N/A | • Review plant selection and irrigation requirements for planted species (e.g. review similar climates through tools such as the Climate Analogues Explorer) |  |  | #N/A |  |  | #N/A
MRD-5 | Dust impacts from quarry - skid resistance, visibility and erosion leading to poor water quality | #N/A | #N/A | • Utilise soil stabilisers. • Cover loads, minimise stockpiles on site. |  |  | #N/A |  |  | #N/A
MRD-6 | Water shortage during prolonged construction phase and operational phase | #N/A | #N/A | • Implement the TMR Water Security and Sustainability Policy. Undertake water balance assessment of future water requirements for infrastructure links. Where water shortages are possible develop water security plant. |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Sea level rise
SLR-1 | Inundation of road formation resulting in disruption to operation | #N/A | #N/A | • Revise the TMR Continuity Network Response Plan to restrict access to critical areas during high tide events and periods of inundation (e.g. shared paths and interchanges) and outline emergency service provisions and response (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
SLR-2 | Permanent inundation of drainage infrastructure reducing the flood immunity of structures | #N/A | #N/A | • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Locate critical infrastructure outside of known low areas and/or flood risk areas |  |  | #N/A |  |  | #N/A
SLR-3 | Exacerbated local flooding risks | #N/A | #N/A | • Apply Road Drainage Manual hydraulic assessment including climate projections. • Revise the TMR Continuity Network Response Plan to restrict access to critical areas (e.g. shared paths) and outline emergency service provisions (e.g. access, notification, etc.) • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Revise the TMR Continuity Network Response Plan to restrict access to critical areas (e.g. interchange) and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
SLR-4 | Ingress of saltwater intrusion into embankment and lower pavement layers causing reduced performance life | #N/A | #N/A | • Raising pavement above projected sea level rise to avoid inundation. |  |  | #N/A |  |  | #N/A
SLR-5 | Increased incidence of coastal erosion, exposing footings and other buried structures, resulting in damage or potential collapse | #N/A | #N/A | • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model Design bridge piles to a Q2000 event • Provide strengthening to existing bridge structures |  |  | #N/A |  |  | #N/A
SLR-6 | Increased incidence of saltwater intrusion, accelerating corrosion of concrete and steel structures | #N/A | #N/A | • Undertake sensitivity checks against modelling utilising RCP 8.5 projections for storm surge, sea level rise and increased rainfall intensity (e.g. Local Government flood model • Provide strengthening to existing bridge structures • Provide additional coverage (e.g. saline resistant covers for electrical systems) / protection (e.g. resistant coatings) of critical structures (e.g. steel or otherwise) |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Extreme heat / Solar Radiation
EH-1 | Damage to electrical system components (e.g. cabling, sensor loops, housings) resulting in disruption smart motorway operation, CCTV and emergency response | #N/A | #N/A | • Investigate the inclusion of backup power or redundant supply (e.g. uninterruptable power supply) for electrical systems as part of design • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Design infrastructure to account for higher temperatures (e.g. increased heat ratings of surfaces / equipment, minimum standards for wire sag) |  |  | #N/A |  |  | #N/A
EH-2 | The accelerated degradation and malfunctioning of electrical equipment, requiring replacement more often, increasing maintenance and operational costs | #N/A | #N/A | • Update maintenance plan to increase the frequency and review of maintenance activities • Design infrastructure to account for higher temperatures (e.g. increased heat ratings of surfaces / equipment, minimum standards for wire sag) • Provide additional coverage (e.g. covers for electrical systems) / protection (e.g. resistant coatings) of critical structures (e.g. steel or otherwise) |  |  | #N/A |  |  | #N/A
EH-3 | The accelerated deterioration of concrete / asphalt infrastructure, resulting in decreased safety for motorists (e.g. potholes) | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information Update maintenance and operations plans to provide for consideration and changes in pavement design (e.g. alternative materials) |  |  | #N/A |  |  | #N/A
EH-4 | The accelerated deterioration of concrete / asphalt / steel infrastructure, resulting in increased maintenance and operational costs (e.g. resurfacing) | #N/A | #N/A | • Update maintenance plan to increase the frequency and review of maintenance activities • Design infrastructure to account for higher temperatures (e.g. increased heat ratings of surfaces / equipment, minimum standards for wire sag) • Update maintenance and operations plans to provide for consideration and changes in pavement design (e.g. alternative materials) • Provide additional coverage (e.g. covers for electrical systems) / protection (e.g. resistant coatings) of critical structures (e.g. steel or otherwise) |  |  | #N/A |  |  | #N/A
EH-5 | Steel structures (e.g. expansion joints, guardrails, bridge components) buckling or warping and impacting safety of users | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information • Revise Standard Operating Procedures to account for extreme heat including provisions for closures of facilities during heatwaves and/or diversions • Investigate mobile phone reception along corridor to support full coverage as manner of emergency response • Provide additional pedestrian / cyclist features such as shade shelters (e.g. shade sails, bench shelters, canopy coverages, etc.) and CCTV to minimise heat related illness • Investigate options for providing relief to cyclists / pedestrians from extreme heat days (e.g. underpass as opposed to bridge, roof structures on bridge) |  |  | #N/A |  |  | #N/A
EH-6 | An increased risk of heat stress for cyclists and pedestrians) using the new facilities | #N/A | #N/A | • Use the Emergency VMS Alert Request and Social Media request forms for warnings and to convey weather hazard information |  |  | #N/A |  |  | #N/A
EH-7 | An increase in the number of vehicle breakdowns along the road (due to vehicle overheating) resulting in safety concerns and increased requirements for road management | #N/A | #N/A | • Revise the TMR Traffic Operations Business Continuity Plan to account for heatwave and extreme heat days including provisions for emergency bays for vehicle breakdowns and/or emergency access / response • Investigate mobile phone reception along corridor to support full coverage as manner of emergency response • Revise / improve notifications and information provided to motorists using the variable message signs • Revise the TMR Continuity Network Response Plan to respond to vehicle breakdowns and outline emergency service provisions (e.g. access, notification, traffic management, etc.) |  |  | #N/A |  |  | #N/A
EH-8 | Adverse impacts to proposed landscaping areas (including those reinstated) including loss of planted species due to ongoing heat exposure | #N/A | #N/A | • Review plant selection and irrigation requirements for planted species (e.g. review similar climates through tools such as the Climate Analogues Explorer) |  |  | #N/A |  |  | #N/A
EH-9 | Increased power demand and/or faults in the network resulting in power supply interruptions and/or outages for electrical infrastructure, including CCTV | #N/A | #N/A | • Design to include additional redundancy in intelligent transportation system infrastructure and smart motorways (e.g. static signs, backup power) • Investigate the inclusion of backup power or redundant supply (e.g. uninterruptable power supply) for electrical systems as part of design |  |  | #N/A |  |  | #N/A
EH-10 | An increased risk to workers during operation from heat stroke, heat stress or heat exhaustion resulting in reduced productivity | #N/A | #N/A | • Revise the TMR Traffic Operations Business Continuity Plan to account for heatwave and extreme heat days including provisions for emergency bays for vehicle breakdowns and/or emergency access / response • Incorporate weather projections and procedures (e.g. wet weather plan) into works scheduling |  |  | #N/A |  |  | #N/A
EH-11 | Increased sag on overhead cables - decreased clearance | #N/A | #N/A | • Design infrastructure to account for higher temperatures (e.g. increased heat ratings of surfaces / equipment, minimum standards for wire sag) • Update maintenance plan to increase the frequency and review of maintenance activities • Revise the TMR Communication Plan / improve notifications and information provided to motorists using the variable message signs |  |  | #N/A |  |  | #N/A
EH-12 | Equipment heat ratings insufficient to meet increased heat | #N/A | #N/A | • Design infrastructure to account for higher temperatures (e.g. increased heat ratings of surfaces / equipment, minimum standards for wire sag) • Update maintenance plan to increase the frequency and review of maintenance activities |  |  | #N/A |  |  | #N/A
| Reduced safety for travelling public due to ITS outages, debris on road, potential damage to assets | #N/A | #N/A | • Revise the TMR Communication Plan / improve notifications and information provided to motorists using the variable message signs |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
| [Project Specific] | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
Other project climate hazard
0 | [Project Specific] | #N/A | #N/A | [Project Specific] |  |  | #N/A |  |  | #N/A
0 | [Project Specific] | #N/A | #N/A | [Project Specific] |  |  | #N/A |  |  | #N/A
|  | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
|  | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A
|  | #N/A | #N/A |  |  |  | #N/A |  |  | #N/A

## Lookups (hidden)
Table 1. AS 5334 Risk Rating Matrix
Likelihood | Insignificant | Minor | Moderate | Major | Severe (Catastrophic)
Almost Certain | Low | Medium | High | Extreme | Extreme
Likely | Low | Medium | Medium | High | Extreme
Possible | Low | Low | Medium | High | Extreme
Unlikely | Low | Low | Medium | Medium | High
Very Unlikely | Low | Low | Low | Medium | Medium
Table 2. Lookups for Project Register.
Likelihood | Consequence
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Very Unlikely | Severe (Catastrophic)
Table 3. Likelihood category descriptions. |  |  |  |  | Table 4. Consequence category descriptions
Likelihood | Description | Recurrent or Event Risks | Long Term Risks |  | Consequence | Adaptive Capacity | Infrastructure, Service | Social / Cultural | Governance | Financial | Environmental | Economy
Almost Certain | Could occur several times per year | Has happened several times in the past year and in each of the previous 5 years; or Could occur several times per year | Has a greater than 90% chance of occurring in the identified time period if the risk is not mitigated |  | Insignificant | No change. | No infrastructure damage, no change to service. | No adverse human health effects. | No changes to management required. | Little financial loss or increase in operating expenses. | No adverse effects on natural environment. | No effects on the broader economy.
Likely | May arise about once per year | Has happened at least once in the past year and in each of the previous 5 years, or may arise about once per year | Has a 61–90% chance of occurring in the identified time period if the risk is not mitigated |  | Minor | Minor decrease to the adaptive capacity of the asset. Capacity easily restored. | Localised infrastructure service disruption. No permanent damage. Some minor restoration work required. Early renewal of infrastructure by 10-20%. Need for new/ modified ancillary equipment. | Short-term disruption to employees, customers, or neighbours. Adverse human health effects. | General concern raised by regulators, requiring response action. | Additional operational costs Financial loss small, <10%. | Minimal effects on the natural environment. | Minor effect on the broader economy due to disruption of service provided by the asset.
Possible | Maybe a couple of times in a generation | Has happened during the past 5 years but not in every year, or May arise once in 25 years | Has a 31–60% chance of occurring in the identified time period if the risk is not mitigated |  | Moderate | Some change in adaptive capacity. Renewal or repair may need new design to improve adaptive capacity. | Limited infrastructure damage and loss of service. Damage recoverable by maintenance and minor repair. Early renewal of infrastructure by 20-50%. | Frequent disruption to employees, customers, or neighbours. Adverse human health effects. | Investigation by regulators Changes to management actions required. | Moderate financial loss 10-50%. | Some damage to the environment, including local ecosystems. Some remedial action. Remediation may be requird. | High impact on the local economy, with some effect on the wider economy.
Unlikely | Maybe once in a generation | May have occurred once in the last 5 years, or May arise once in 25 to 50 years | Has a 6-30% chance of occurring in the future if the risk is not mitigated |  | Major | Major loss in adaptive capacity. Renewal or repair would need new design to improve adaptive capacity | Extensive infrastructure damage requiring major repair. Major loss of infrastructure service. Early renewal of infrastructure by 50-90%. | Permanent physical injuries and fatalities may occur. Severe disruptions to employees, customers or neighbours. | Notices issued by regulators for corrective actions. Changes required in management. Senior management Responsibility questionable. | Major financial loss 50-90%. | Significant effect on the environment and local ecosystems. Remedial action likely to be required. | Serious effect on the local economy spreading to the wider economy
Very Unlikely (Rare) | Maybe once in a lifetime | Has not occurred in the past 5 years; or Unlikely during the next 50 years | May occur in exceptional circumstances, i.e. less than 0-5% chance of occurring in the identified time period if the risk is not mitigated |  | Severe (Catastrophic) | Capacity destroyed, redesign required when repairing or renewing asset | Significant permanent damage and/or complete loss of the infrastructure and the infrastructure service. Loss of infrastructure support and translocation of service to other sites. Early renewal of infrastructure by 90%. | Severe adverse human health effects, leading to multiple events of total disability or fatalities. Total disruption to employees, customers or neighbours. Emergency response at a major level. | Major policy shifts. Change to legislative requirements | Extreme financial loss > 90%. | Very significant loss to the environment. May include localised loss of species, habitats or ecosystems. Extensive remedial action essential to prevent further degradation. Restoration likely to be required. | Major effect on the local, regional and state economies.